|  |  |
| --- | --- |
| **KEY OBJECTIVES**   * **To measure the impact of literacy interventions in DASP schools** * **Ensure best practice is embedded across all DASP schools** | **SUCCESS CRITERIA**   * **An audit and evaluation of current success rates in reading interventions** * **By Spring 2015 produce an Action Plan (with training) for improvements in reading interventions** * **By the end of 2015/16 reduce the number of pupils in Year 2 who have not reached “ARE” in reading by X%** |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Actions** | **Timescale** | **Accountability** | **Outcome** | | **Budget/Resources** | **Monitoring/Review/Impact** |
| Employ L Keys for one day per week Dec – July as Literacy Consultant  To carry out audit of practice in each DASP school | Feb – July  Dec - Feb | Literacy Group  Literacy Group |  | | £200 x 24  £2000 to cover potential training implications | Report back to LG and Heads on half termly basis |
| To analyse impact of current interventions and produce a data report of AR reading levels by:   * Pyramid * Mini-Pyramid * School by school | By March | Literacy Group |  | | £150 to cover support from DG | Headteachers meetings |
| Produce action to cover summer term | End of March | Literacy Group |  | |  | Headteachers meetings |
| **KEY OBJECTIVE**   * **To raise the status of reading for pleasure (i.e. not just “can” read but “want” to read)** | | | | **SUCCESS CRITERIA**   * **To raise levels of enjoyment in reading by X** | | |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Actions** | **Timescale** | **Accountability** | **Outcome** | **Budget/Resources** | **Monitoring/Review/Impact** |
| Carry out reading survey to collect baseline data | Register by end of October and complete by end of November 2014 | Literacy Group | All schools to carry out and share survey results for:  Year 4  Year 7  Year 9 | Nil | (see results)  Repeat survey in 2015 |
| Peer writing project using Story Bird and/or What Pad (ICT)   * Competition | Spring term 2015 | Literacy Group  (Fiona Brady) | All Year 9 students to produce opening chapter | Transport costs –  £100  Prizes £200 | * Publications available in all schools * At least 20% of students tell us it has made them more likely to write creatively or read for enjoyment. |
| Continue with book clubs/reading challenge/  recommended reading | Nov – June 2015  June | Literacy Group | Every school has active Book Club  Recommended read booklet distributed | £100 per school to fund each Book Club  £250 prizes  £2000 printing costs | 50% of pupils in First Schools take part in summer Reading Challenge. |
| Reading/Literacy Festival to raise profile of reading in DASP community | End of June 2015 | Literacy Group | DASP Reading Week with 3 guest speakers for each phase (THS Theatre) + parent involvement | £2000 | Attitudinal survey for parents (part of Literacy Trust survey) |