|  |  |
| --- | --- |
| **KEY OBJECTIVES*** **To measure the impact of literacy interventions in DASP schools**
* **Ensure best practice is embedded across all DASP schools**
 | **SUCCESS CRITERIA*** **An audit and evaluation of current success rates in reading interventions**
* **By Spring 2015 produce an Action Plan (with training) for improvements in reading interventions**
* **By the end of 2015/16 reduce the number of pupils in Year 2 who have not reached “ARE” in reading by X%**
 |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Actions** | **Timescale** | **Accountability** | **Outcome** | **Budget/Resources** | **Monitoring/Review/Impact** |
| Employ L Keys for one day per week Dec – July as Literacy ConsultantTo carry out audit of practice in each DASP school |  Feb – JulyDec - Feb |  Literacy GroupLiteracy Group |   |  £200 x 24£2000 to cover potential training implications | Report back to LG and Heads on half termly basis |
| To analyse impact of current interventions and produce a data report of AR reading levels by:* Pyramid
* Mini-Pyramid
* School by school
 | By March | Literacy Group |  | £150 to cover support from DG | Headteachers meetings |
| Produce action to cover summer term | End of March | Literacy Group |  |  | Headteachers meetings |
| **KEY OBJECTIVE*** **To raise the status of reading for pleasure (i.e. not just “can” read but “want” to read)**
 | **SUCCESS CRITERIA*** **To raise levels of enjoyment in reading by X**
 |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Actions** | **Timescale** | **Accountability** | **Outcome** | **Budget/Resources** | **Monitoring/Review/Impact** |
| Carry out reading survey to collect baseline data | Register by end of October and complete by end of November 2014 | Literacy Group | All schools to carry out and share survey results for:Year 4Year 7Year 9 | Nil | (see results)Repeat survey in 2015 |
| Peer writing project using Story Bird and/or What Pad (ICT)* Competition
 | Spring term 2015 | Literacy Group(Fiona Brady) | All Year 9 students to produce opening chapter | Transport costs – £100Prizes £200 | * Publications available in all schools
* At least 20% of students tell us it has made them more likely to write creatively or read for enjoyment.
 |
| Continue with book clubs/reading challenge/recommended reading | Nov – June 2015June | Literacy Group | Every school has active Book ClubRecommended read booklet distributed | £100 per school to fund each Book Club£250 prizes£2000 printing costs | 50% of pupils in First Schools take part in summer Reading Challenge. |
| Reading/Literacy Festival to raise profile of reading in DASP community | End of June 2015 | Literacy Group | DASP Reading Week with 3 guest speakers for each phase (THS Theatre) + parent involvement | £2000 | Attitudinal survey for parents (part of Literacy Trust survey) |